## for publication (hidden)
Work Packages | Activities Main Description | Max. Available Budget (EUR) | Financial offer by the tenderer
2.1.1 | Developing extension plans according to GAPs | 0 | ____________________________
2.1.2 | Training of Trainers | 0 | ____________________________
2.1.3 | Providing technical and financial assistance for rolling out the extension plans | 0 | ____________________________
Total Cost (EUR) |  | 0 | ____________________________
Expected Output/Result 2.2 - Animal wealth resources are improved and diversified
Work Package | Activities Main Description | Max. Available Bbudget (EUR) | Financial offer by the tenderer
2.2.1 | Increasing knowledge of the situation of the animal husbandry | 0 | ____________________________
2.2.2 | Buiding the capacity of veterinary providers & raising awareness to veterinary services | 0 | ____________________________
2.2.3 | Improving profitability of the animal husbandry | 0 | ____________________________
Total Cost (EUR) |  | 0 | ____________________________
Overall Total Cost for Lot 1(EUR) |  | 0
NB: i) The overall financial offer by the tender cannot be above the maximum available budget. ii) Variations within the budget breakdown allocations are allowed, for as long as they are within 5% (less or more) of the allocated maximum available budget.

## Service
Expected Output/Result 2.1 - The extension system is strengthened towards a sustainable management of natural resources and agrifood-ecosystems
Work Packages | Activities Main Description | Max. Available Budget (EUR) | Financial offer by the tenderer
2.1.1 | Developing extension plans according to GAPs | 136050.0206 | ____________________________
2.1.2 | Training of Trainers | 126250.2 | ____________________________
2.1.3 | Providing technical and financial assistance for rolling out the extension plans | 1048128.4 | ____________________________
Total Cost (EUR) |  | 1310428.6206 | ____________________________
Expected Output/Result 2.2 - Animal wealth resources are improved and diversified
Work Package | Activities Main Description | Max. Available Budget (EUR) | Financial offer by the tenderer
2.2.1 | Increasing knowledge of the situation of the animal husbandry | 2800 | ____________________________
2.2.2 | Buiding the capacity of veterinary providers & raising awareness to veterinary services | 315255 | ____________________________
2.2.3 | Improving profitability of the animal husbandry | 123796.58 | ____________________________
Total Cost (EUR) |  | 441851.58 | ____________________________
Overall Total Cost for Lot 1(EUR) |  | 1752280.2006
NB: i) The overall financial offer by the tender cannot be above the maximum available budget. ii) Variations within the budget breakdown allocations are allowed, for as long as they are within 5% (less or more) of the allocated maximum available budget.

## 2.1.1
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Developing extension plans according to GAPs. 2.1.1 | Preparation of updated current extension programmes including extension plans for the application of GAPs to the identified crops in 3 targeted governorates (Beni Suef , Assiut and Sohag) as follows: |  |  |  | 0
| Provide experts to develop a total of 26 new extension plans to the identified crops. | No. of extenstions | 26
| Each new extension program must be accompanied by a package of: - Digital awareness material for farmers (non-printed) in a visual format with drawings and illustrations - 1 Animation videos up to 3 minutes each with Arabic voice over and English subtitles and 1 Eeducational film demonstrating good agriculture practices (5min, with animation and promos in Arabic language, with English subtitles) based on extension messages. - Promoting the digital awareness materials on Facebook by launching 18 digital awareness campaigns Awarness campaignes to be shared with the official pages of Agriculture directorates at each governorates. | No. of Packages | 26
| Written approval for devloped material in collaboartion with the relevant research institutes for the developed material before utilization. | Lump Sum | Lump Sum
| Create pool of expert involving all the specialized national and international experts notably with the support of the ARC Research Institutes to prepare the extension plans while preparing a database for the group with its specializations. | Lump Sum | Lump Sum

## 2.1.2
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Training of Trainers. 2.1.2 | Providing intensive training programmes to the extension providers at institutional central and governorate levels for the application of the GAPs including climate smart agriculture practices, in 3 targeted governorates (Beni Suef, Assiut and Sohag) as follows: |  |  |  | 0
| Provide training experts to carry out 50 trainings courses for 330 trainees in 445 training days in Beni Suef, Assiut, and Sohag | No. of training Days | 445
| Preparing training materials for identified crops using the extension programs related to outcomes of the results( 2.1.1) in three governorates in 100 days maximum | No. of training Days | 100
| Transportation allowances for Trainees | No. of Trainees | 330
| Meals for Trainees | No. of Trainees | 330
| Training logistics services (equipping training halls - stationery) | No. of Courses | 178

## 2.1.3
| TOTAL 2.1.3 (A+B+….+G) - EURO |  |  |  | 0
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Providing technical and financial assistance for rolling our the extension plans. 2.1.3 | A) - Providing technical and financial assistance for applying GAPs and better agricultural services through training programmes, field days, and farmer field schools (FFS), in 3 targeted governorates (Beni Suef , Assiut and Sohag) as follows: |  |  |  | 0
| Provide training experts to carry out 11 training courses to 330 trainees in 66 days n Beni Suef, Assiut, and Sohag | No. of Training Days | 66
| Preparing training materials for qualifying FFS facilitators in three governorates,( using FAO Farmer Field School Guidance) | No. of Training Days | 5
| Preparing the qualifying FFS facilitators training report on each governorates. | No. of Training Days | 6
| Transportation allowances for Trainees (FFS facilitators) | No. of Trainees | 330
| Trainees per meals(FFS facilitators) | No. of Trainees | 330
| Training/courses logistics services (equipping training halls - stationery) | No. of Courses | 11
| Provide national training experts to implement and supervise 600 FFS in the targeted governorates, which includes the following specializations (team leader, field crop expert, agriculture economist, and field coordinators).The team will work in cooperation with the Agricultural Extension Department in each governorate.Costs include accommodation and transportation in the governorates | No. of Training Days | 150
| A total number of 600 farmer field schools (FFS) at 200 FFS per target governorate that will be approved by EU-Zira3a. The FFS will be held with the participation of 20 farmers, the farmer field school facilitator will hold 12 sessions/season for each FFS.The cost includes: - meals for participants of farmers- stationery and promotional materials - transportation allowance for FFS facilitators. | No. of FFS | 600
| Prepare final report documenting all FFS conducted activities, practices (Arabic & English). | No. of Days | 12
| Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
| B) - Establish 600 demonstration/educational fields (1 Feddan each) attached to each FFS to organize farmer field days to provide training and GAPs practical applications including climate-smart agriculture in the 3 targeted governorates |  |  |  | 0
| Each demonstration/educational field will be supported by selected seeds, agricultural mechanization and biofertilizers, under the full supervision of the FFS s field crop experts. | No. of Demonstration Fields | 600
| Final report documenting the economic impact analysis for the educational fields and its comparison to traditional fields under the full supervision of the FFSs agriculture economist and FFSs field coordinators (Arabic & English) for each targeted governorate | No. of Working Days | 15
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Providing technical and financial assistance for rolling our the extension plans. 2.1.3 | C) - Providing a specific extension programme as part of raising the awareness of farmers and Water Users Associations regarding the best use of irrigation water |  |  |  | 0
| Provide an expert to prepare the extension programme on the best use of irrigation water to raise awareness of farmers and WUAs | No. of Working Days | 5
| Provide 6 experts ( 2 per each governorate ) to carry out the 90 Awareness sessions (each expert to hold 15 Awareness sessions ) on the best use of irrigation water to raise awareness of farmers and WUAs. It includes accommodation and transportation costs in the targeted governorates | No. of Awareness Sessions | 90
| Carry out the 90 Awareness sessions for WUAs and farmers regarding the best use of irrigation water. The costs of awareness session day include: Break meal farmers and Training logistics services (equipping training halls - stationery and promotional materials ) | No. of Awareness Sessions | 90
| Prepare final report documenting all Awareness sessions conducted per each governorate (Arabic & English). | No. of Working Days | 6
| Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
| D) - Implement a digital platform with the use of new mobile application for the dissemination of extension plans (WP 2.1.1) covering the selected crops and challenges faced in the targeted governorates |  |  |  | 0
| Provide an expert to produce of mobile application(s) for extension services .It includes accommodation and transportation costs in the targeted governorates | No. of Working Days | 30
| Testing, evaluating and updating the application | No. of Working Days | 10
| Final report for mobile application | No. of Working Days | 4
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Providing technical and financial assistance for rolling our the extension plans. 2.1.3 | E) - Design 6 field demonstration models for modern on-farm irrigation systems in the old lands in 3 targeted governorates (Beni Suef , Assiut and Sohag) as follows: |  |  |  | 0
| Situation analysis (Institutional and technical) of the current irrigation systems in the selected sites ( 5 feddan per site per governorate - total of 3 sites in the targeted governorates).It includes accommodation and transportation costs in the targeted governorates | No. of Working Days | 20
| Documentation of low-cost solutions for small scale irrigation systems available in the national and international market | No. of Working Days | 5
| Detailed technical design with drawings including solar power ,pump houses and bill of quantities of the 3 sites with complete material and cost estimates and technical specifications.It includes accommodation and transportation costs in the targeted governorates | No. of Working Days | 21
| Feasibility report for the implantation of modern irrigation system & Business model for solar power in Old lands-Egypt | No. of Working Days | 5
| Prapare Performance Monitoring and Maintenance Plan for Solar-powered Modern Irrigation Systems in the 3 sites. | No. of Working Days | 6
| Implementation of 3 sites of modern on-farm irrigation systems. It includes accommodation and transportation costs in the targeted governorates | No. of Working Days | 30
| Farmers training in 3 targeted governorates.It includes accommodation and transportation costs in the targeted governorates | No. of Working Days | 20
| extension officers training in 3 targeted governorates | No. of Working Days | 20
| Evaluation of the sustainability of improved irrigation systems (Scalability assessment) | No. of Working Days | 5
| Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
| F) - Forming water user associations and raise their knowledge by trainings on water saving issues in 3 targeted governorates (Beni Suef , Assiut and Sohag) as follows: |  |  |  | 0
| Conduct 60 preparatory meetings with farmers at the meskas level and elect the WUAs board of directors and registration of 60 new WUAs according to Irrigation and Drainage Law amended by Law No. 213 (1994) and its executive regulations 14900 of year 1995 | No. of Meetings | 60
| Conduct 9 training courses for members of the boards of directors of new water user associations on Irrigation and Drainage Law amended by Law No. 213 (1994) and its executive policy No. 14900/1995. The cost includes preparing the training material, consultant fees, training halls, office supplies, and break meals for trainees, transportation and accommodation for training consultants. | No. of Trainings | 9
| Follow up and assist WUAs in day-to-day management and execution of tasks based on WUA policy and procedures including transportation, accommodation and reporting. | No. of Working Days | 40
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Providing technical and financial assistance for rolling our the extension plans. 2.1.3 | G) - Establishment of 6 field demonstration models and pilots for modern on-farm irrigation systems in the old lands,including supply tools and materials of water pumping system powered by solar energy and provide training in the 3 targeted governorates (Beni Suef , Assiut and Sohag) as follows: |  |  |  | 0
| Supplying, transporting and installing a solar energy system mounted on a metal structure 3 to 4 m height and to be above the roof of the pump room. | No. of Solar Energy System | 6
| Supply, transportation and installation of a centrifugal pump powered by electricity (solar energy), with a total dynamic lift greater than 45 m, pumps (with a theoretical flow rate of 15 L sec-1), in addition to the pump, a motor will be installed on a chassis. | No. of Centrifugal Pump | 6
| Supply and installation of a sand and disc filtration unit (36-4) with a flow rate of 150 m3/h with a filtration efficiency of 120-130 mesh or complete mesh filters with air valves, safety and control, pressure meters, fertilization connections, main underground lines for entry and exit, automatic backwash, and the concrete base. | No. of Sand & Disc Filtration Unit | 6
| Supplying and making concrete bases, making a circular pull pit of regular concrete, 30 cm thick, with a height of 25 cm to the highest ground level. | No. of Concrete Bases | 6
| Supplying, pouring and making a complete 3 x 5 m room for all pumps and filters. | No. of Rooms | 6
| Surveillance cameras for the pump room, solar cells and control unit | No. of Cameras | 24
| Supply, installation, connection and testing of UPVC pipes at 6 atmosphere pressure for the main, sub-main and subsidiary lines. | lumpsum | 6
| Supply, transportation and installation of a single and sub-control unit to connect the main and sub-main line with a 4-inch valve, and a double control unit to connect the main sub-main and the manifolds . | lumpsum | 6
| Polyethylene hoses (Plain hoses 16mm P.E and GR polyethylene hoses 16 mm hoses, 30 cm, 4 L/h flow rate. ) | lumpsum | 6
| Polyethylene installation supplies (Grommet at the beginning of the line 16 mm P.E + rubber,Tee 16 mm P.E,16 mm P.E. connector and End of line 16 mm P.E | lumpsum | 6
| 20 HP reserve diesel pump, (30 m3/hour) ,In case it is necessary to complete the irrigation process at night | No. of Diesel Pumps | 6
| H) - Implement field trials of improved Seeds/ cultivars of fodderin 3 targeted governorates (Beni Suef , Assiut and Sohag) as follows: |  |  |  | 0
| Provide an expert to implement at least 60 field trials of fodder of sorghum - alfalfa - millet - fodder cowpeas - fodder beets (1 feddans per each ) in 3 targeted governorates (Beni Suef , Assiut and Sohag), including the final report. | No. of field trials | 60

## 2.2.1
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Promoting the diversification of livestock 2.2.1 | A) - Promoting the diversification of livestock |  |  |  | 0
| Provide an expert ( Team Leader - livestock expert) to carry out a study for promoting the diversification of livestock, taking into account the following points: Collecting data and information on the situation of the animal husbandry in each governorate. Mapping of the associations specialized in animal production in each governorate. Detect the diversity of the local strains and assess their tolerability to climate change conditions. Investigate the strength of the local breeds of animals in the three governorates with changing environmental conditions. Improving local strains of meat and milk through cross-breeding with other high-quality breeds. Risk assessment of loss of genetic diversity of the local strains. | No. of Working Days | 16
| B) - Preparing technical awareness materials for use in awareness campaigns for farmers towards diversifying livestock through training specialists | No. of Working Days | 2

## 2.2.2
| TOTAL 2.2.2 (A+B+….+G) - EURO |  |  |  | 0
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Buiding the capacity of veterinary providers & raising awareness to veterinary services 2.2.2 | A) - Providing training on rapid and early diagnosis of infectious, epidemiological, and transboundary diseases, in 3 targeted governorates (Beni Suef , Assiut and Sohag) as follows: |  |  |  | 0
| Provide training experts to carry out the training programs for veterinary services providers in target governorates on rapid and early diagnosis of infectious, epidemiological, and transboundary diseases. | No. of Training Days | 55
| Preparing training materials on rapid and early diagnosis of infectious, epidemiological, and transboundary diseases. | No. of Working Days | 5
| Preparing training report for each governorate. | No. of Working Days | 5
| Transportation allowances for Trainees (veterinary services providers ) | No. of Trainees | 220
| Meals for Trainees (veterinary services providers ) | No. of Trainees | 220
| Training logistics services (equipping training halls - stationery) at 3 targeted governorates | No. of Courses | 11
| Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
| B) - Providing training to the veterinary services providers on veterinary treatments, vaccination and artificial insemination in 3 targeted governorates (Beni Suef , Assiut and Sohag) as follows: |  |  |  | 0
| Provide training experts to carry out the training programs for veterinary services providers in target governorates on veterinary treatments, vaccination (cost includes the accommodation and transportation). | No. of Training Days | 55
| Preparing training materials on rapid and early diagnosis of infectious, epidemiological, and transboundary diseases. | No. of Working Days | 5
| Preparing training report for each governorate. | No. of Working Days | 5
| Transportation allowances for Trainees (veterinary services providers ) | No. of Trainees | 220
| Meals for Trainees (veterinary services providers ) | No. of Trainees | 220
| Training logistics services (equipping training halls - stationery) at 3 targeted governorates | No. of Courses | 11
| Conducting an agreement with the Animal Reproduction Research Institute to train and implement practical training programs for veterinary service providers in the targeted governorates on artificial insemination of cows and buffalos. | No. of Courses | 18
| Accommodation cost in Giza for Trainees (veterinary services providers )- Full board with meals | No. of Trainees | 180
| Transportation allowances to Giza and comeback for Trainees (veterinary services providers ) | No. of Trainees | 180
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Buiding the capacity of veterinary providers & raising awareness to veterinary services 2.2.2 | C) - Provide training on pregnancy monitoring and follow up for veterinary service providers in the targeted governorates |  |  |  | 0
| Conducting an agreement with the Animal Reproduction Research Institute (ARRI) to train and implement practical training programs for veterinary service providers in the targeted governorates on Use of ultrasound to monitor pregnancy in cows and buffalos. | No. of Courses | 18
| Accommodation cost in Giza for Trainees (veterinary services providers )- Full board with meals | No. of Trainees | 180
| Transportation allowances to Giza and comeback for Trainees (veterinary services providers ) | No. of Trainees | 180
| D) - Raising awareness (by campaigns and visibility/promotional materials) of smallholder farmers regarding the advantages of the artificial insemination and vaccination, in 3 targeted governorates (Beni Suef , Assiut and Sohag) as follows: |  |  |  | 0
| Provide an expert (Team Leader - livestock expert) to prepare scientific veterinary technical materials in order to design two packages of awareness materials for farmers. | No. of Working Days | 8
| Provide a graphic designer expert to design 2 packages of awareness materials for farmers (non-printed) in visual form with drawings and illustrations on the advantages of artificial insemination and vaccinations. | No. of Packages | 2
| Printing awareness materials for farmers on the advantages of artificial insemination and vaccinations (3000 poster and 3000 flyers) | No. of Awareness Materials | 6000
| Sharing and promoting awareness materials (by the team leader) in the targeted areas via the pages of veterinary medicine directorates on Social Media in the targeted governorates, according to the time plan and awareness standards agreed upon with the program. Up to 21 digital campaigns in the three governorates. | No. of Awarness Days | 30
| Provide 12 experts ( 4 per each governorate ) under the supervision of the team leader to carry out the 180 Awareness sessions. | No. of Awareness Sessions | 180
| Carry out the 180 Awareness sessions (2400 faremers) regarding the advantages of artificial insemination and vaccinationsr to raise awareness of farmers . The costs of awareness session day include: Break meal farmers and Training logistics services (equipping training halls - stationery and promotional materials ) | No. of Awareness Sessions | 180
| Prepare final report documenting all Awareness sessions conducted per each governorate (Arabic & English). | No. of Working Days | 6
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Buiding the capacity of veterinary providers & raising awareness to veterinary services 2.2.2 | E) - Carrying out a updated assessment about needs of veterinary medicine and vacinations at directorates in the targeted governorates (Beni Suef , Assiut and Sohag) and assessment of materials and equipment needed (e.g. sampling tools) to improve and disseminate artificial insemination through services providersas follow: |  |  |  | 0
| Provide an expert to carry out updated assessment to determine the needs of veterinary medicine at directorates in the targeted governorates (Beni Suef , Assiut and Sohag) and assessment of materials and equipments needed to improve and disseminate artificial insemination (desk research and field visits, including final report). | No. of Working Days | 6
| Prapare Performance Monitoring and Maintenance Plan for liquid nitrogen production units | No. of Working Days | 3
| F) - Providing veterinary medicines through implementing veterinary therapeutic convoys to small scale farmers for the most common diseases in targeted governorates. |  |  |  | 0
| Conducting an agreement with the Animal Reproduction Research Institute to implementing veterinary therapeutic convoys to small scale farmers for the most common diseases in the targeted governorates. The cost of the convoy includes accommodation and food for the veterinary team, in addition to logistical equipment for the location of the veterinary convoy, in addition to the costs of all means of transportation, whether between governorates or internal transportation. | No. of Veterinary Convoys | 160

## 2.2.3
| TOTAL 2.1.3 (A+B+….+E) - EURO |  |  |  | 0
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Improving profitability of the animal husbandry 2.2.3 | A) - Promoting the diversification of livestock,in 3 targeted governorates (Beni Suef , Assiut and Sohag) as follows: |  |  |  | 0
| Provide 12 experts ( 4 per each governorate ) under the supervision of the team leader to carry out the 180 Awareness sessions ( one expert hold 15 Awareness sessions ) on promoting the diversification of livestock,to raise awareness of farmers. | No. of Awareness Sessions | 180
| Carry out the 180 Awareness sessions (2400 faremers) regarding the promoting the diversification of livestock,to raise awareness of farmers . The costs of awareness session day include: Break meal farmers and Training logistics services (equipping training halls - stationery and promotional materials) | No. of Awareness Sessions | 180
| Prepare final report documenting all Awareness sessions conducted per each governorate (Arabic & English) | No. of Working Days | 6
| Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
| B) - Disseminate updated plans for improving nutrition status and raising of the Egyptian buffalo (enhanced males) |  |  |  | 0
| Provide an expert to update plans for improving nutrition status and raising of the Egyptian buffalo (enhanced males) in 3 targeted governorates (Beni Suef , Assiut and Sohag), including final report. | No. of Working Days | 25
| Holding workshops ( 1 day/ governorate) for livestock engineers and agricultural extension workers to present the updated plans for improving nutrition status and raising of the Egyptian buffalo (enhanced males). The cost of the workshop includes: (hall rent - breakfast and lunch for participants - office training supplies - training logistics - consultant accommodation ,transportation and fees) | No. of Workshops | 3
Result /WP | Activities | Unit | Total No. Units | Unit Value EUR | Total Cost EUR
Improving profitability of the animal husbandry 2.2.3 | C) - Provide training farmers including women to upgrade their skills and knowledge of the integrated dairy value chains according to EU, EFSA, and CODEX standards, |  |  |  | 0
| Provide an expert ( Team Leader ) to prepare technical training materials for farmers including women to upgrade their skills and knowledge of the integrated dairy value chains | No. of Working Days | 10
| Provide 12 experts ( 4 per each governorate ) under the supervision of the team leader to carry out the 180 awarness sessions on upgrade farmers skills and knowledge of the integrated dairy value chains. | No. of awareness sessions | 180
| Carry out the 180 awareness sessions for farmers including women (2400 farmers)to upgrade their skills and knowledge of the integrated dairy value chains. The costs of training session day include: Break meal farmers and Training logistics services (equipping training halls - stationery and promotional materials ) | No. of awareness sessions | 180
| Prepare final report documenting all training sessions conducted per each governorate (Arabic & English). | No. of Working Days | 6
| D) - Produce and disseminate materials to raise the awareness of improving hygiene awareness to avoid losses in milk production |  |  |  | 0
| Provide an expert (Team Leader - livestock expert) to prepare scientific technical materials in order to design package of awareness materials for farmers on improving hygiene awareness to avoid losses in milk production. | No. of Working Days | 15
| Provide a graphic designer expert to design awareness materials for farmers (non-printed) in visual form with drawings and illustrations on improving hygiene awareness to avoid losses in milk production, the package contains (1 poster, 1 flyer, 4 Facebook posts, 2 audio/animated animation, 10 seconds , 1 animation video of up to 3 minutes each with Arabic audio commentary and English subtitles. | No. of Packages | 2
| Printing awareness materials for farmers on improving hygiene awareness to avoid losses in milk production (3000 poster and 3000 flyers) | No. of Awareness Materials | 6000
| Sharing and promoting awareness materials in the targeted areas via the pages of veterinary medicine directorates on Social Media in the targeted governorates, according to the time plan and awareness standards agreed upon with the programme. Up to 21 digital campaigns in the three governorates. | No. of Digital Campaigns | 21
| Provide 12 experts ( 4 per each governorate ) under the supervision of the team leader to carry out the 180 Awareness sessions on improving hygiene awareness to avoid losses in milk production to raise awareness of farmers . | No. of Awareness Sessions | 180
| Carry out the 180 Awareness sessions (2400 faremers) regarding on improving hygiene awareness to avoid losses in milk production to raise awareness of farmers . The costs of awareness session day include: Break meal farmers and Training logistics services (equipping training halls - stationery and promotional materials ) | No. of Awareness Sessions | 180
| Prepare final report documenting all Awareness sessions conducted per each governorate (Arabic & English). | No. of Working Days | 6
Improving profitability of the animal husbandry 2.2.3 | E) - Advocating farmers to be part of a dairy collection and processing centre to facilitate products marketing so as to improve their profit. |  |  |  | 0
| Provide a expert to conduct a study on how to invite farmers to be part of a milk collection and processing center to facilitate marketing of the products to improve their profits. | No. of Working Days | 12
| Final Report | No. of Working Days | 3